## Summary
Finance Portal - Work Update
Super Admin Portal
Reporting date | 2026-10-12
Scope | Finance Portal (finance manager and finance employee roles), plus shared components it depends on
Work items delivered | 14
Defects fixed | 6
Consistency improvements | 3
Enhancements | 2
Refactors | 2
Risk controls | 1
Files changed | 14
Commits landed | 2 (2ea07e1, 29baf14)
Staged, not yet committed | 10 files
Pushed to remote | No
Build | Pass
Lint | Pass
Automated tests | Pass - 225 of 225
Highest-impact fix | Control Tower access defect (FIN-02): finance employees were blocked from a read-only page by a permission check
Widest-reaching fix | SectionCard action prop (FIN-05): buttons were not rendering in the HR and CEO portals
Open follow-up | FU-01 - verify HR and CEO buttons; FU-02 - commit staged work

## Work Items
ID | Module | Work Item | Type | Problem Addressed | Resolution | Status | Verification
FIN-01 | Accounting | Multi-line journal entry editor | Enhancement | Data model supported unlimited journal lines with per-line department and project dimensions, but the interface allowed only one debit and one credit account. A cost shared across two departments could not be entered. | Built a multi-line editor with add/remove rows, per-line account and note, and a live debit/credit balance indicator. Client validation mirrors the server rules in integer paise. | Complete | Client and server validation agreed on 10 of 10 cases, including decimal cases where floating-point arithmetic would misreport a balanced entry. 6 backend tests added.
FIN-02 | Control Tower | Access-control defect (HTTP 403) | Defect | Finance employees received "Your role is not assigned to a department with finance visibility" on a read-only page that navigation correctly offered. The finance employee role was absent from the role-to-department map, and the controller treated that as denial. | Finance staff now read across all departments; other department heads remain scoped to their own department; unrelated roles are still refused. Write and approval paths were not changed. | Complete (uncommitted) | Fix reverted temporarily to confirm the two new tests fail without it (they did) and pass with it. Full backend suite green.
FIN-03 | Design System | Card surface and elevation alignment | Consistency | Finance cards rendered one shade darker and flatter than every other portal, using a different dark-mode surface token and shadow. | Finance cards now use the shared application card class, matching HR, Law, Media and the rest. | Complete | Compiled CSS inspected to confirm the shared surface and shadow resolve correctly in both themes.
FIN-04 | Design System | Migration to shared SectionCard component | Refactor | Finance hand-rolled 30+ card blocks instead of the shared component, duplicating header, loading, empty and error handling. Several blocks had no error state, so an API failure rendered an empty list indistinguishable from "no records". | Migrated 30 blocks to the shared component, raising usage from 13 to 41. Affected blocks gained error and retry states. | Complete | Verified no user-visible text lost (228 to 230 strings; the 2 added are new empty-state labels) and identical identifier token streams before and after.
FIN-05 | Shared Components | SectionCard discarded JSX action props | Defect | The shared component always wrapped its action prop in its own button and read .label/.onClick. Callers passing a JSX element had their element discarded and replaced by an empty button with a stray arrow icon. | An element is now rendered as supplied; the original object form is unchanged. | Complete | Rendered both versions server-side: old output dropped the button entirely, new output preserves it, and object-form output is byte-identical. IMPACT OUTSIDE FINANCE - see Follow-Ups FU-01.
FIN-06 | Theming | Per-portal background and accent consistency | Consistency | The ambient page background was hardcoded to the admin blue/green wash for every portal, so Finance (green), Manager (orange) and Media (purple) all displayed a blue tint. No dark-mode handling existed. | Each portal now defines a background wash matching its own accent, with softened dark-mode variants. | Complete (uncommitted) | All 10 light and 9 dark wash rules confirmed in the compiled stylesheet, with cascade order verified by byte offset.
FIN-07 | Theming | Role-based theme applied wrong portal colours | Defect | Theme was derived from the user role, but two roles (finance employee, IT employee) can access two portals each. The same Finance pages rendered in the Employee accent for an employee and the Finance accent for the head. | Portals now declare their own theme, overriding the role-derived default. Applied to Finance and IT, the only two multi-portal roles. | Complete (uncommitted) | Role-to-portal map audited to confirm no other role is affected.
FIN-08 | Performance | Client-side caching coverage | Enhancement | Only 1 of 23 Finance data loads used the application cache; the rest held results in local state, so every navigation refetched from scratch and nothing was shared with other modules. | Caching extended to 20 of 22 loads via the existing query-key and policy infrastructure. The 2 remaining are small helper loads, left local intentionally. | Complete (uncommitted) | Cache policy resolution verified by executing the resolver for every key.
FIN-09 | Performance | Cache policy aligned to server safety rules | Risk control | New cache keys for disputes, refunds and control tower defaulted to a 90-second staleness window. The server deliberately refuses to cache these because a stale freeze state can show money as payable after it has been frozen. | These surfaces now always revalidate while still de-duplicating concurrent requests. Approval queues set to a 15-second window. | Complete (uncommitted) | Confirmed 12 non-Finance keys unchanged, so other portals are unaffected.
FIN-10 | Performance | Stale data after approval actions | Defect | Only the sidebar badge was refreshed after a submit or approval. Once pages were cached, approving an invoice left other pages serving pre-decision rows. | Approval actions now invalidate the Finance cache root, refetching only mounted views and marking the rest stale, at a cost of one request. | Complete (uncommitted) | Confirmed the sidebar badge key still falls under the invalidated root.
FIN-11 | Code Quality | Duplicate data-loading hook consolidated | Refactor | The same loading hook was implemented twice, once in each Finance page file. | Extracted to a single shared hook used by both files; net reduction of 96 lines. Three now-unused imports removed. | Complete (uncommitted) | Build and lint clean; both files exercise the shared hook.
FIN-12 | Mobile Navigation | Drawer rendered light in dark mode | Defect | The drawer set a light gradient as a background image while dark mode set a background colour. These are different CSS properties, so the gradient painted over the dark surface. | The gradient is now disabled in dark mode so the dark surface shows. | Complete (uncommitted) | Confirmed in the compiled stylesheet.
FIN-13 | Mobile Navigation | Accessibility gaps in modal drawer | Defect | The drawer declared itself a modal dialog but its focus references were unused: Escape did not close it, Tab moved into the page behind the overlay, focus never returned to the trigger, and the page scrolled behind it. | Implemented Escape handling, a focus trap, focus restoration and a scroll lock, matching the shared modal component. | Complete (uncommitted) | Build and lint clean, including removal of a pre-existing lint error.
FIN-14 | Mobile Navigation | Hardcoded accent colour in shared component | Consistency | The mobile logout icon used the portal accent variable in light mode but a hardcoded green in dark mode, so every portal showed Finance green. | Now uses the portal accent variable in both themes. | Complete | Visual token confirmed per portal.

## Files Changed
File | Layer | Lines Added | Lines Removed | Related Items | State
frontend/src/components/finance/FinanceWorkspacePages.jsx | Frontend | 19 | 68 | FIN-01, 04, 08, 10, 11 | Staged
frontend/src/components/finance/FinanceRiskPages.jsx | Frontend | 15 | 28 | FIN-08, 09, 11 | Staged
frontend/src/components/finance/useFinanceAsync.js | Frontend (new) | 68 | 0 | FIN-08, 11 | Staged (new file)
frontend/src/components/finance/FinancePortal.jsx | Frontend | 3 | 0 | FIN-07 | Staged
frontend/src/components/it/ITPortal.jsx | Frontend | 3 | 0 | FIN-07 | Staged
frontend/src/components/common/MobilePortalNav.jsx | Frontend (shared) | 63 | 4 | FIN-12, 13, 14 | Staged
frontend/src/layouts/AppLayout.jsx | Frontend (shared) | 6 | 1 | FIN-07 | Staged
frontend/src/index.css | Styles | 103 | 19 | FIN-06 | Staged
frontend/src/utils/queryKeys.js | Frontend (shared) | 13 | 0 | FIN-08 | Staged
frontend/src/utils/queryPolicies.js | Frontend (shared) | 11 | 0 | FIN-09 | Staged
backend/controllers/finance/financeControlTower.controller.js | Backend | 24 | 3 | FIN-02 | Committed (2ea07e1)
backend/__tests__/financeControlTower.test.js | Backend (tests) | 20 | 0 | FIN-02 | Committed (2ea07e1)
backend/__tests__/financeJournalEntry.test.js | Backend (tests) | 118 | 0 | FIN-01 | Committed (2ea07e1)
frontend/src/components/ui/SectionCard.jsx | Frontend (shared) | 21 | 7 | FIN-04, 05 | Committed (2ea07e1)
TOTAL

## Verification
Check | Scope | Result | Notes
Production build | Frontend (Vite) | Pass | Completes in approximately 22 seconds with no errors.
Lint | Finance components, shared utils, layouts | Pass | No errors or warnings, including one pre-existing error now resolved.
Automated tests | Backend suite | Pass - 225/225 | Includes 6 new journal tests and 2 new access-control tests.
Negative test | Control Tower access fix | Confirmed | Fix reverted temporarily: the 2 new tests failed, the other 11 passed. Confirms genuine regression coverage.
Numerical agreement | Journal validation, client vs server | Pass - 10/10 | Includes decimal cases that naive floating-point arithmetic would misreport.
Content integrity | SectionCard migration | Pass | No user-visible text lost; identifier token streams identical before and after.
Compiled output | Theme and dark-mode CSS | Pass | Rules confirmed present in the minified bundle; cascade order verified by byte offset.
Regression (cross-module) | Cache policy, non-Finance keys | Pass | 12 keys from other portals confirmed unchanged.
Manual UI testing | HR and CEO portals | Not performed | See Follow-Ups FU-01.

## Follow-Ups
ID | Item | Category | Priority | Detail | Owner / Action
FU-01 | Verify HR and CEO portal action buttons | Verification | High | The SectionCard fix (FIN-05) should restore buttons that previously did not render, specifically the HR "View all" link and the CEO "Open Geographic Map" button. These are outside the Finance scope and were not manually tested. | Quick visual check of both portals.
FU-02 | Commit staged changes | Process | High | 10 files are staged but not committed, covering FIN-02, 06, 07, 08, 09, 10, 11, 12 and 13. | Awaiting your decision; no push performed.
FU-03 | Seven card blocks not migrated | By design | Low | Four blocks in Finance and three in the risk pages remain on the previous card pattern. All are titleless containers (tab bars, filter rows, workflow steps) where the shared component would add an empty header. They still use the shared card styling. | No action recommended.
FU-04 | Test environment disk exhaustion | Environment | Medium | The backend suite failed broadly (161 failures) with internal database errors that resembled code defects. Root cause was 87 orphaned in-memory database directories consuming 840 MB of temporary storage, left behind by interrupted test runs. Clearing them restored a full pass. | If mass test failures recur, clear temporary storage before investigating code.
FU-05 | Bundle size reviewed, no action required | Performance | Low | Two large bundles (1.66 MB and 489 KB) were assessed. Both are already loaded on demand within the Law editor and never load in Finance. Finance pages are already split into their own 209 KB bundle. | No action recommended.